## Risk Register
TechNova Ltd - Information Security Risk Register ¦ ISO 27005:2022 · ISO 31000:2018
Assessment Date: May 2026 ¦ Next Review: August 2026 ¦ Risk Owner: CTO / GRC Lead ¦ Version: 1.0 ¦ Status: DRAFT - Pending Management Review
RISK IDENTIFICATION | [5 empty] | INHERENT RISK |  |  |  | EXISTING CONTROLS | RESIDUAL RISK |  |  |  | TREATMENT |  | OWNERSHIP & TRACKING |  |  | REFERENCE
Risk ID | Category | Asset / Asset Group | Threat | Vulnerability | Risk Scenario | Likelihood (Inherent) | Impact (Inherent) | Score (Inherent) | Rating (Inherent) | Existing Controls | Likelihood (Residual) | Impact (Residual) | Score (Residual) | Rating (Residual) | Treatment Option | Treatment Actions / Gap Analysis Ref | Risk Owner | Target Date | Status | ISO 27001 Ref | Next Review
▶ GOVERNANCE & COMPLIANCE
R-001 | Governance & Compliance | ISMS / Policies | Regulatory non-compliance | No ISMS, no IS policy suite, no risk assessment process in place | TechNova fails an NHS/G-Cloud supplier audit due to absence of ISO 27001 controls, resulting in removal from procurement frameworks and loss of public sector contracts. | 4 | 4 | 16 | HIGH | No ISMS. SOC 2 Type I provides limited assurance. No IS policy suite exists. | 3 | 3 | 9 | MEDIUM | Modify (Reduce) | Establish ISMS (GA-004). Implement IS Policy Suite (GA-020). Conduct gap analysis (this document). Pursue ISO 27001 certification. Assign GRC Lead resource. | CTO / Board | Q3 2026 | Open | 4.4, 5.1, 5.2 | 2026-08-01
R-002 | Governance & Compliance | Legal & Regulatory | GDPR enforcement action | Incomplete data mapping, no tested DSAR process, production PII in test environments | A data subject complaint triggers an ICO investigation. TechNova cannot demonstrate GDPR compliance, resulting in a formal reprimand or fine (up to 4% global turnover / £17.6M ARR equivalent). | 3 | 5 | 15 | HIGH | GDPR registration exists. Privacy notice published. AWS BAA in place. Basic DPA clause in client contracts. | 2 | 4 | 8 | MEDIUM | Modify (Reduce) | Complete ROPA/data flow mapping (GA-077). Test DSAR process (30-day SLA). Prohibit production data in test (GA-060, GA-072). Appoint Data Protection Lead. | GRC Lead / Legal | Q3 2026 | Open | A.5.34 | 2026-08-01
R-003 | Governance & Compliance | Cyber Insurance | Insurance coverage gap | No evidence of controls required by insurer; controls not documented for renewal | At cyber insurance renewal, TechNova cannot evidence required controls (MFA, patching, BCP). Insurer declines renewal or imposes exclusions, leaving the company uninsured for cyber incidents. | 3 | 4 | 12 | HIGH | Cyber insurance in force. MFA via Okta partially deployed. CloudTrail active. | 2 | 3 | 6 | MEDIUM | Modify (Reduce) | Document and evidence: MFA coverage (GA-054), vulnerability management (GA-057), BCP (GA-045). Prepare insurance evidence pack prior to renewal. | CTO / GRC Lead | Q3 2026 | Open | 5.1, 6.1 | 2026-08-01
▶ ACCESS CONTROL
R-004 | Access Control | All systems (Okta SSO) | Credential compromise / account takeover | MFA not enforced for all applications; some legacy integrations use username/password | An attacker obtains staff credentials via phishing. Lack of MFA on legacy integrations allows account takeover, leading to exfiltration of client data from M365 or Jira. | 4 | 4 | 16 | HIGH | Okta SSO deployed. MFA enforced for most apps. AWS console MFA enforced. | 2 | 3 | 6 | MEDIUM | Modify (Reduce) | Audit all apps for MFA enforcement (GA-054). Eliminate shared accounts. Replace legacy integrations. Target 100% MFA. Deploy phishing-resistant MFA (FIDO2) for admin accounts. | IT | Q3 2026 | Open | A.5.15, A.5.17 | 2026-08-01
R-005 | Access Control | AWS IAM / Cloud | Privilege escalation / IAM misconfiguration | No PAM tooling; privileged access not formally reviewed; IAM policies not audited against least privilege | An engineer with broad AWS IAM permissions (or a compromised engineer account) escalates privileges, accesses production data stores, and exfiltrates client database contents. | 3 | 5 | 15 | HIGH | AWS IAM roles in use. MFA on AWS console. Some IAM policies in place. | 2 | 4 | 8 | MEDIUM | Modify (Reduce) | Conduct privileged access review (GA-051). Implement IAM least privilege audit (AWS IAM Access Analyzer). Deploy AWS IAM Identity Center for JIT access. Implement CloudTrail alerting on privilege escalation. | DevOps Lead | Q3 2026 | Open | A.5.15, A.8.2 | 2026-08-01
R-006 | Access Control | All systems | Insider threat - data theft by employee/contractor | No DLP; contractors have access to source code and client data; no user behaviour analytics | A disgruntled employee or contractor deliberately exfiltrates client data or source code prior to leaving, causing reputational damage, client loss, and potential legal liability. | 2 | 5 | 10 | MEDIUM | GitHub branch protection. Okta SSO access controls. Some access review performed. | 2 | 4 | 8 | MEDIUM | Modify (Reduce) | Implement DLP (GA-061). Review contractor access (GA-053). Implement UBA/SIEM monitoring (GA-062). Time-limit contractor access. Enforce NDA (GA-086). Improve offboarding (GA-030). | IT / GRC Lead | Q3 2026 | Open | A.5.3, A.8.12 | 2026-08-01
R-007 | Access Control | All systems | Failure to revoke access on departure | Joiner/mover/leaver process is manual and inconsistently followed; no automated deprovisioning | A former employee retains active credentials to corporate systems post-departure. Access is used maliciously or inadvertently to access client data or sabotage systems. | 4 | 4 | 16 | HIGH | Okta SSO centralises access. HR offboarding checklist exists informally. | 2 | 3 | 6 | MEDIUM | Modify (Reduce) | Automate JML via Okta Lifecycle Management (GA-035). Define offboarding SLA: all access revoked within 1 hour of departure. Implement quarterly access recertification (GA-037). Monthly orphaned account review. | IT / HR | Q3 2026 | Open | A.5.16, A.5.18 | 2026-08-01
▶ CLOUD INFRASTRUCTURE
R-008 | Cloud Infrastructure | AWS environment | AWS misconfiguration | No security baseline; AWS Config rules not comprehensive; no drift detection; no Well-Architected Review | An AWS misconfiguration (e.g. S3 bucket publicly accessible, security group overly permissive, RDS snapshot publicly shared) exposes client data to the internet. | 3 | 5 | 15 | HIGH | AWS Config partially enabled. GuardDuty active. CloudTrail enabled. Terraform IaC used. | 2 | 4 | 8 | MEDIUM | Modify (Reduce) | Implement CIS AWS Benchmark via AWS Config rules (GA-058). Enable AWS Security Hub (CSPM). Conduct AWS Well-Architected Review (GA-040). Set up S3 Block Public Access at account level. Enable drift detection alerts. | DevOps Lead | Q3 2026 | Open | A.8.9, A.5.23 | 2026-08-01
R-009 | Cloud Infrastructure | AWS / GitHub | Supply chain attack on CI/CD pipeline | No SAST/SCA in CI/CD; no SBOM; third-party GitHub Actions not pinned to digest | Malicious code is injected into a third-party GitHub Action or npm dependency. The compromised package is built into the production application, creating a backdoor or exfiltrating secrets. | 3 | 5 | 15 | HIGH | GitHub private repos. Branch protection enabled. Code review via PRs. | 2 | 4 | 8 | MEDIUM | Modify (Reduce) | Pin all GitHub Actions to commit digest. Implement SCA (Snyk/Dependabot) (GA-067). Produce SBOM (GA-038b). Enable GitHub secret scanning. Review third-party Action permissions. Implement SLSA framework. | DevOps Lead | Q3 2026 | Open | A.5.21, A.8.25 | 2026-08-01
R-010 | Cloud Infrastructure | AWS (all services) | Ransomware / destructive attack | No immutable backups; no tested recovery procedure; no network segmentation preventing lateral movement | A ransomware attack encrypts production databases and backups. TechNova cannot restore services within client SLA, resulting in breach of contract, reputational damage, and potential platform shutdown. | 2 | 5 | 10 | MEDIUM | RDS automated backups. S3 versioning partially enabled. Multi-AZ RDS. AWS GuardDuty for threat detection. | 1 | 5 | 5 | LOW | Modify (Reduce) | Enable S3 Object Lock (immutable backups) (GA-100). Test RDS restoration quarterly. Implement network segmentation (GA-106). Deploy AWS Backup with cross-account backup copy. Develop ransomware response playbook (GA-043). | DevOps Lead | Q4 2026 | Open | A.8.13, A.5.29 | 2026-08-01
R-011 | Cloud Infrastructure | AWS Secrets / GitHub | Secrets and credentials exposed in code | No systematic secret scanning; developers may commit API keys, passwords, or tokens to version control | An AWS access key or third-party API secret is committed to a GitHub repository (even briefly). An automated scanner or attacker discovers it and uses it to access production systems or third-party services. | 4 | 4 | 16 | HIGH | GitHub private repos. Some awareness of secrets management. Terraform state managed in S3. | 2 | 3 | 6 | MEDIUM | Modify (Reduce) | Enable GitHub secret scanning and push protection (GA-053). Deploy AWS Secrets Manager for all application secrets (GA-036). Audit historical commits for exposed secrets. Implement pre-commit hooks (git-secrets or trufflehog). | DevOps Lead | Q3 2026 | Open | A.8.9, A.8.28 | 2026-08-01

## Risk Heat Map
TechNova Ltd - Risk Heat Map ¦ Inherent Risk Positions
Each cell shows Risk IDs positioned by Likelihood (rows) × Impact (columns). Inherent risk before controls applied.
◄ IMPACT ►
LIKELIHOOD | 1 Negligible | 2 Minor | 3 Moderate | 4 Significant | 5 Catastrophic
5 Almost Certain
4 Likely |  |  |  | R-001 R-004 R-007 R-011
3 Possible |  |  |  | R-003 | R-002 R-005 R-008 R-009
2 Unlikely |  |  |  |  | R-006 R-010
1 Rare
LEGEND
| CRITICAL (20-25) | HIGH (12-19) | MEDIUM (6-11) | LOW (3-5) | VERY LOW (1-2)
◄ RESIDUAL RISK POSITIONS (after treatment) ►
LIKELIHOOD | 1 Negligible | 2 Minor | 3 Moderate | 4 Significant | 5 Catastrophic
5 Almost Certain
4 Likely
3 Possible |  |  | R-001
2 Unlikely |  |  | R-003 R-004 R-007 R-011 | R-002 R-005 R-006 R-008 R-009
1 Rare |  |  |  |  | R-010

## Methodology
TechNova Ltd - Information Security Risk Register
Methodology & Risk Criteria ¦ Frameworks: ISO 27005:2022 · ISO 31000:2018 · ISO 27001:2022 Annex A
1. PURPOSE & SCOPE
Purpose | This Risk Register documents the outputs of TechNova Ltd's first formal information security risk assessment, conducted in accordance with ISO 27005:2022 (IS risk management) and ISO 31000:2018 (risk management principles). It supports the establishment of the ISMS required by ISO 27001:2022 Clause 6.1.
Scope | The risk assessment covers all information assets within the ISMS scope: AWS cloud environment (eu-west-2 primary, eu-central-1 DR), Manchester HQ, remote workers (UK and Poland), and all systems used to deliver the TechNova SaaS platform.
Approach | Asset-based risk assessment: identify assets → identify threats and vulnerabilities per asset → assess likelihood and impact → calculate inherent risk → select treatment → assess residual risk. Scenario-based threats aligned to MITRE ATT&CK, NCSC guidance, and ENISA Threat Landscape.
Review Cycle | Risk register reviewed: (1) annually as part of management review, (2) following any significant IS incident, (3) upon material change to the organisation, infrastructure, or threat landscape, (4) prior to any significant new product launch or third-party engagement.
2. RISK SCORING METHODOLOGY (ISO 27005:2022)
Likelihood Scale (1–5) | 1=Rare (<5% chance / once in 10+ years) ¦ 2=Unlikely (5-20% / once in 5-10 years) ¦ 3=Possible (20-50% / once in 2-5 years) ¦ 4=Likely (50-80% / once per 1-2 years) ¦ 5=Almost Certain (>80% / more than once per year)
Impact Scale (1–5) | 1=Negligible (minimal disruption, no data loss, <£10k cost) ¦ 2=Minor (short disruption, limited PII, £10k-£100k) ¦ 3=Moderate (significant disruption, <500 records, £100k-£500k, regulatory notice) ¦ 4=Significant (major breach, 500-10k records, £500k-£2M, regulatory fine) ¦ 5=Catastrophic (existential threat, >10k records, >£2M, loss of certification/clients)
Risk Score Formula | Risk Score = Likelihood × Impact ¦ Range: 1–25 ¦ Inherent Risk = before controls ¦ Residual Risk = after treatment controls applied
3. RISK RATING MATRIX (HEAT MAP)
LIKELIHOOD → | 1 Negligible | 2 Minor | 3 Moderate | 4 Significant | 5 Catastrophic
5 Almost Certain | 5 | 10 | 15 | 20 | 25
4 Likely | 4 | 8 | 12 | 16 | 20
3 Possible | 3 | 6 | 9 | 12 | 15
2 Unlikely | 2 | 4 | 6 | 8 | 10
1 Rare | 1 | 2 | 3 | 4 | 5
4. RISK RATING LEGEND & RESPONSE REQUIREMENT
CRITICAL (20–25) | Immediate escalation to board. Treatment plan within 5 business days. Interim controls required immediately. CEO/CTO must be notified.
HIGH (12–19) | Escalate to CTO/senior management. Treatment plan within 30 days. Tracked at every management review.
MEDIUM (6–11) | Risk owner to implement treatment within 90 days. Reviewed quarterly. Acceptable with documented compensating controls.
LOW (3–5) | Monitor and review annually. Accept with owner sign-off. No immediate action required if controls are adequate.
VERY LOW (1–2) | Accept. Review annually as part of routine risk register update.
5. TREATMENT OPTIONS (ISO 27005:2022 Clause 8.5)
Modify (Reduce) | Implement or strengthen controls to reduce likelihood and/or impact to an acceptable level. Most common treatment. Links to Annex A controls and Gap Analysis remediation.
Retain (Accept) | Accept the risk at its current level. Requires documented justification, risk owner sign-off, and confirmation that residual risk is within appetite. Must be reviewed annually.
Avoid | Cease the activity that gives rise to the risk. Appropriate when risk cannot be reduced to acceptable levels and the activity is not business-critical.
Share (Transfer) | Transfer risk to a third party: cyber insurance, contractual liability transfer, or outsourcing. Does not eliminate the risk - residual risk and third-party risk remain.
6. RISK APPETITE STATEMENT
Overall Appetite | TechNova Ltd has a LOW risk appetite for information security risks that could result in: (1) unauthorised disclosure of client or employee personal data, (2) loss of availability of the SaaS platform exceeding 4 hours, (3) regulatory sanction from the ICO or loss of G-Cloud/NHS framework status, (4) reputational damage affecting client retention.
Tolerances | CRITICAL risks: zero tolerance - must be treated immediately. HIGH risks: tolerated only with approved interim controls and treatment plan. MEDIUM risks: tolerated with documented owner acceptance. LOW/VERY LOW: accept without formal treatment unless cost-effective controls available.
Disclaimer | TechNova Ltd is a fictional company created for portfolio purposes. All risks, scores, and owners are simulated based on the fictional company profile.